**ACTION PLAN**

**FOR**

**THE CONTROL OF AIR POLLUTION**

**IN**

 **KHURJA CITY**

****

**REGIONAL OFFICE**

**UTTAR PRADESH POLLUTION CONTROL BOARD**

**F-5, JAMUNAPURAM COLONY, BULANDSHAHAR**

**1. INTRODUCTION**

 Khurja is a city (and a [municipal board](https://en.wikipedia.org/wiki/Municipal_board)) in the [Bulandshahr district](https://en.wikipedia.org/wiki/Bulandshahr_district) in the Indian [state](https://en.wikipedia.org/wiki/States_and_territories_of_India) of [Uttar Pradesh](https://en.wikipedia.org/wiki/Uttar_Pradesh). It is situated around 85 km from [Delhi](https://en.wikipedia.org/wiki/Delhi). Khurja supplies a large portion of the ceramics used in the country, hence it is sometimes called The Ceramics City. The town is also famous for its special sweet, known as "khurchan". The name Khurja is derived from the [Urdu](https://en.wikipedia.org/wiki/Urdu) word kharija meaning, cancelledor condemned, as the revenue for this town was waived because this land included many swamps and the agricultural possibilities were rare.

 Khurja is now famous for its ceramics. With over 500 factories producing [ceramic](https://en.wikipedia.org/wiki/Ceramic) works, its skyline is dotted with [chimneys](https://en.wikipedia.org/wiki/Chimneys). Khurja is located at [28.25°N 77.85°E](https://tools.wmflabs.org/geohack/geohack.php?pagename=Khurja&params=28.25_N_77.85_E_). It has an average elevation of 197 metres (646 foot).A s per provisional data of 2011 census, Khurja urban agglomeration had a population of 142,636, out of which males were 75,384 and females were 67,252. The development activities of U.P. Small Industrial Corporation Ltd. resulted in setting up of UPSIC Potteries Ltd. in 1976–77. There was a widespread complaint about the efficiency of the UPSIC Potteries Ltd., primarily because of high costs. The Government of Uttar Pradesh set up a panel in Nov.1990 to examine the working of the corporation and to consider the proposal of the passing of the commercial activities back to the Pottery Development Centre (Local Office of Directorate of Industries).

 Though an industrial region, Khurja lacks the infrastructure for good industry by European standards. Since there are often power cuts lasting around eight hours, all factories and most homes have private generators. The municipality water supply is insufficient or everybody's need so many have water pumps to extract groundwater. The city is located at 28.2514° N, 77.8539° E

 Air pollution has been viewed seriously by the Hon'ble Supreme Court, Hon'ble High Court & Hon'ble National Green Tribunal and issued specific directions from time to time for the improvement the air quality of the city. Central Pollution Control Board has also issued direction under section 18 (1)(b) of the Air (Prevention & Control of Pollution) Act 1981, regarding prevention, control or abatement of Air pollution in various cities of Uttar Pradesh including Khurja.

**2. ACTION TAKEN BY THE BOARD**

 Board has issued directions to Principal Secretary Urban Development, Principal Secretary Forests, Principal Secretary Transport, Principal Secretary Agriculture, Managing Director Central U.P. Gas Ltd., Managing Director Indraprastha Gas Ltd, and Managing Director Green Gas Ltd. under section 31 (A) of the Air (Prevention and Control of Pollution) Act, 1981 regarding prevention and control of air pollution in Khurja city on dated 05.09.2016 in compliance of directions issued by Central Pollution Control Board, Delhi under section 18(1) (b) of the Air (Prevention and Control of Pollution) Act, 1981.

 Ambient Air is being monitored regularly by the Board. At source emission monitoring i.e. stack monitoring of industries is also being done regularly and action is being taken accordingly on the basis of analysis report. If any industry is found violating the standards firstly show-cause notice is issued to the industry followed by closure under Air (Prevention and Control of Pollution) Act, 1981.

**3. ANNUAL AVERAGE DATA OF AMBIENT AIR QUALITY PM10 (µg/m3) OF KHURJA CITY**

 U.P. Pollution Control Board is monitoring ambient air quality of Khurja city manually at 02 locations viz. CGCRI Campus and Ahirpara for PM10, SO2 and NO2 parameters. Annual Average data of Ambient Air Quality particularly PM10 (Particulate Matter size less than 10 microns) were observed during the year 2013-18 are as given below.

|  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
| **S.No.** | **Name of Location** | **Category** | **2013** | **2014** | **2015** | **2016** | **2017** | **2018** |
| 1 | CGCRI Campus | Industrial | 174.4 | 173.2 | 181.2 | 176.0 | 204.8 | 212.75 |
| 2. | Ahirpara | Residential | 148.2 | 141.2 | 153.6 | 163.9 | 180.1 | 196.54 |
|  | STANDARD(annual average)  |  | 60 µg/m3   |

**4. SOURCES OF POLLUTION IN KHURJA**

 **T**he main sources of air pollution in Khurja city are Vehicular, Road dust, Construction & Demolition activities, Industries (Point source & Areas source), Garbage burning & Agriculture waste burning etc. Data obtained from Manual monitoring under National Ambient Monitoring Programme (NAMP) (2018) at Khurja showed values of NO2 19.80(µg/m3) and SO2 21.27 (µg/m3) at CGCRI Campus and ; NO2 18.60(µg/m3) and SO2 19.97 (µg/m3) at Ahirpara.

**5. Short term & Long term Action Plan**

1. **Vehicle emission control**
2. **Long Term Action Plan: Reduce congestion**

|  |  |  |  |
| --- | --- | --- | --- |
| **Sl. No** | **Action Points** | **Timeframe for implementation** | **Action Required to be Taken by Responsible Departments** |
| i | Plying of electric buses for public transport including establishment of sufficient charging stations. | 360 days | Transport Department |
| ii | Prepare plan for construction of expressways/bypasses to avoid congestion due to non-destined vehicles. | 360 days | N.H.A.I. /PWD |
| iii | Construction of peripheral road around the city to avoid congestion. | 360 days | N.H.A.I./PWD |
| iv | Arrangement of Multilevel Parking Facilities | 360 days | Nagar Nigam/Development Authorities |
| v | Development/Strengthening of Bike zone/Cycle zone at metro/railways/bus stations from where travelers hire bi- cycle to reach the destination. | 360 days | Nagar Nigam/Development Authorities |
| vi | Initiate steps for retrofitting of particulate filters in diesel vehicles, when BS-VI fuels are available | 360 days | Vehicle Manufacturing Companies/Ministry of Road Transport & Highways (MoRTH) |
| vii | Use of Bio-Ethanol in the city/urban transport system/waste to energy. | 360 days | Transport Department |
|

|  |
| --- |
| **(b) Short Term Action Plan**  |
| **Sl. No** | **Action Points** | **Timeframe for implementation** | **Action Required to be Taken by Responsible Departments** |
| i | Launch extensive drive against polluting vehicles for ensuring strict compliance | As regular activity | R.T.O/Traffic Police |
| ii | Launch public awareness campaign for air pollution control, vehicle maintenance, minimizing use of personal vehicles, lane discipline, etc. | As regular activity | R.T.O/ Traffic Police |
| iii | Prevent parking of vehicles in the non-designated areas | As regular activity | Traffic Police/ Nagar Nigam |
| iv | Prepare & implement action plan to check fuel adulteration and random monitoring of fuel quality data | 30 days | District Supply Officer/Oil companies |
| v | Prepare & implement plan for widening of roads and improvement of infrastructure for decongestion of road | 90 days | Nagar Nigam |
| vi | Steps for promoting battery operated vehicles including establishment of charging stations. | 120 days | Transport Department/Nagar Nigam & Development Authorities |
| vii | Install weigh in motion bridges at the borders of cities/towns and States to prevent overloading of vehicles | 180 days | Transport Department |
| viii | Synchronize traffic movements/Introduce intelligent traffic systems for lane-driving | 180 days | Traffic Police |
| ix | Installation of remote sensor based PUC system | 180 days | Traffic Police |

 |

1. **Suspension of road dust and other fugitive emissions control**

**(a)Long Term Action Plan**

|  |  |  |  |
| --- | --- | --- | --- |
| **Sl. No.** | **Action Points** | **Timeframe for implementation** | **Action Required to be Taken by Responsible Departments** |
| **i)** | Implementation of maintaining at least 33% forest cover area in the city in master plan. | 360 days | Nagar Palika Parishad, Khurja /Devlopment Authority/Forest Department |
| **ii)** | All the canals/nullah's side roads should be brick lined. Proper plantation also carried out.  | 360 days | Irrigation Department/ Forest Department/NMCG |

1. **Short Term Action Plan**

|  |  |  |  |
| --- | --- | --- | --- |
| **Sl. No.** | **Action Points** | **Timeframe for implementation** | **Action Required to be Taken by Responsible Departments** |
| **i)** | Prepare plan for creation of green buffers along the traffic corridors. Plantation of specific types of species of plants which are helpful in pollution control. | 90 days | Forest Department/Horticulture/ Nagar Palika Parishad, Khurja & Development Authorities |
| **ii)** | Maintain potholes free roads for free-flow of traffic | 90 days & as regular activity afterwards. | Nagar Palika Parishad, Khurja / Development Authorities |
| **iii)** | Introduce water fountains at major traffic intersection, wherever feasible | 90 days | Nagar Palika Parishad, Khurja |
| **iv)** | Greening of open areas, gardens, community places, schools and housing societies | 90 days | Forest Department |
| **v)** | Blacktopping of metalled road including pavement of road shoulders | 180 days | Nagar Palika Parishad, Khurja |
| **vi)** | Use of treated effluent of STPs in Pollution Control Measure such as watering of Plants, sprinkling for dust suppression purposes. | 90 days | Nagar Palika Parishad |
| **vii)** | Wall to Wall pavement for control of dust from road. Design the footpath pavement/tiles having capacity to grow grass in between.  | 180 days | Nagar Palika Parishad |

**(C)Control of emissions from biomass/crop residue/garbage/municipal solid waste burning**

|  |  |  |  |
| --- | --- | --- | --- |
| **Sl. No.** | **Action Points** | **Timeframe for implementation** | **Action Required to be Taken by Responsible Departments** |
| **i)** | Launch extensive drive against open burning of bio-mass, crop residue, garbage, leaves, etc. | 90 days | Nagar Palika Parishad |
| **ii)** | Regular check and control of burning of municipal solid wastes and use of fire extinguisher for control of fire in municipal solid waste and bio mass. | Nagar Palika Parishad |
| **iii)** | Proper collection of horticulture waste (bio-mass) and its disposal following composting-cum-gardening approach | Nagar Palika Parishad |
| **iv)** | Ensure ban on burning of agriculture waste and crop residues and its implementation | 180 days | Agriculture Department & U.P. Pollution Control Board |
| **v)** | Door to Door collection of segregated waste by agency and then its disposal directly in plant without dumping it on land. | 90 days | Nagar Palika Parishad, Khurja  |
| **vi)** | Establishment of composting pits in Parks/ residential societies etc for management of biodegradable waste. | 90 days | Nagar Palika Parishad, Khurja / Development Authority |
| **vii)** | No plot should be left open more than 02 years and planting of trees must be mandatory on vacant plots. | 90 days | Nagar Palika Parishad, Khurja / Development Authority |

1. **Control of industrial emissions**

**(a) Long Term Action Plan**

|  |  |  |  |
| --- | --- | --- | --- |
| **Sl. No.** | **Action Points** | **Timeframe for implementation** | **Action Required to be Taken by Responsible Departments** |
| i) | Conversion of natural draft brick kilns to induced draft using zigzag technique in a phased manner. | 360 days | U.P. Pollution Control Board |
| ii) | Installation of Electrostatic precipitators and appropriate air pollution control devices in factory units/industries.  | 180 days | U.P. Pollution Control Board |
| iii) | Development of mobile facility/van for continuous ambient air quality monitoring for different localities. | 360 days | Nagar Nigam |

**(b) Short Term Action Plan**

|  |  |  |  |
| --- | --- | --- | --- |
| **Sl. No.** | **Action Points** | **Timeframe for implementation** | **Action Required to be Taken by Responsible Departments** |
| i) | Identification of brick kilns and their regular monitoring including use of designated fuel, and closure of unauthorized units | 60 days | U.P. Pollution Control Board |
| ii) | Conversion of natural draft brick kilns to induced draft | 120 days | U.P. Pollution Control Board |
| iii) |  Monitoring of industrial emission including real time online monitoring through OCEMS (Online Continuous Emission Monitoring System) and live camera feed and to take action against non-complying industrial units. | 60 days, and thereafter, regular activity | U.P. Pollution Control Board  |
| iv) | Bank guarantee should be taken for the compliance of conditions imposed in CTO/CTE for control of Environmental Pollution from industries. The bank guarantee shall be forfeited in case of any violation. Verification of these conditions to be carried out by UPPCB/selected Third Party Institutions/Quality control agencies etc. | 60 days, and thereafter, regular activity | U.P. Pollution Control Board  |
| v) | Installation of web cams and OCEMS in Grossly Polluting Industries.  | 60 days | U.P. Pollution Control Board |

1. **Control of air pollution from constructions and demolition activities**

|  |  |  |  |
| --- | --- | --- | --- |
| **Sl. No.** | **Action Points** | **Timeframe for implementation** | **Action Required to be Taken by Responsible Departments** |
|  i) | Enforcement of Construction & Demolition Rules 2016. Fine should be imposed on defaulting units. | 15 days , and thereafter, continue as regular activity | Urban Development/Development Authorities |
| ii) | Control measures for fugitive emissions from material handling, conveying and screening operations through water sprinkling, curtains, barriers and dust suppression units; | Urban Development/Development Authorities |
| iii) | Ensure carriage of construction material in closed/covered vessels | Development authorities/ Regional Transport Department |
| iv) | Environmental aspects should be included during preparation of master plan for development of city.  | Within a reasonable timeframe | Urban Development/Development Authorities |
| v)  | Builders should leave 33% area for green belt in residential colonies. Plantation should be done as per Office order No.H16405/220/2018/02 dated 16.02.201 available on website of the Board .i.e.,www.uppcb.com. | Within a reasonable timeframe | Urban Development/Development Authorities/ housing companies |
| vi) | All construction areas must be covered to avoid dispersion of particulate matter | 30 days | Nagar Nigam/Development Authorities |

1. **Other Steps to control Air Pollution**

**(a) Long Term Action Plan**

|  |  |  |  |
| --- | --- | --- | --- |
| **Sl. No.** | **Action Points** | **Timeframe for implementation** | **Action Required to be Taken by Responsible Departments** |
| **i)** | Dead Bodies of Animals should be disposed through proper treatment facility like rendering plant etc | 360 days | Nagar Palika Parishad, Khurja |
| **ii)** | Installation of CAAQMS by polluting units/institutions etc. under "Polluters Pay Principles". | 360 days | U.P. Pollution Control Board |
| **iii)** |  Source Apportionment, Emission Inventory & Carrying Capacity Assessment  | 4 years | U.P. Pollution Control Board |
| **iv)** | Tree Plantation for mitigation of air pollution based open location of pollution sources and Windrose data | 360 days | Forest department/Development Authority/IMD/Regional Office & UPPCB |

1. **Short Term Action Plan**

|  |  |  |  |
| --- | --- | --- | --- |
| **Sl. No.** | **Action Points** | **Timeframe for implementation** | **Action Required to be Taken by Responsible Departments** |
| **i)** | Air Quality Index to be calculated and disseminated to the people through website and other media (on maximum fortnightly basis for manually operated monitoring stations and real time basis for continuous monitoring stations | 15days, and thereafter, continue as regular activity | U.P. Pollution Control Board |
| **ii)** | Establish an Air Quality Management Division at SPCB/PCC Head Quarters to oversee air quality management activities in the State and interact with CPCB | 30 days | U.P. Pollution Control Board |
| **iii)** | Set-up and publicize helpline in the city/town as well as SPCB/PCC HQ for complaints against reported non-compliance | 30 days | U.P. Pollution Control Board |
| **iv)** | Engage with concerned authorities on continual basis for maximizing coverage of LPG/PNG for domestic and commercial cooking with target of 100% coverage | 30 days | District Supply Officer |
| **v)** | Monitoring of DG sets and action against violations Fine should be imposed on defaulters. | 30 days | U.P. Pollution Control Board/Nagar Palika Parishad, Khurja |
| **vi)** | Street vendors are to be controlled strictly in respect of removing their wastes and debris before leaving the site of operation | 30 days | Nagar Nigam/Development Authorities |
| **vii)** | Complete ban on littering of streets with municipal solid wastes (MSW). Segregation & source collection at source of MSW to be implemented. | 30 days | Nagar Nigam/Development Authorities |
| **viii)** | If Air Quality Index found severe or above grade, ensure availability of masks to public for protection.  | 90 days | Nagar Palika Parishad, Khurja |