## Sheet 1 - Nahar BMC Forest Crea
Nahar BMC Forest Creation Schedule
S.No. | Activities | Start Date | End Date | Primary Role | Support Role | Status (X= Incomplete/ongoing, O = Complete) | Remarks
Pre Execution Technical Components
1 | Contract finalisation, bringing Afforestt on board as consultants. | 2019-07-16 | 2019-07-16 | Client and Afforestt |  | O
2 | Site visit to check for site readiness. | 2019-07-23 | 2019-07-23 | Afforestt |  | O
3 | Soil sample collection. | 2019-08-05 | 2019-08-05 | Afforestt | Client | O
4 | Site readiness check-sheet onsite review. | 2019-08-06 | 2019-08-06 | Client and Afforestt |  | O
5 | Soil Study and analysis. | 2019-08-06 | 2019-08-12 | Afforestt |  | O
6 | Soil nourishment materials research, selection and quantification. | 2019-08-06 | 2019-08-12 | Afforestt |  | O
7 | Soil analysis and soil nourishment materials detailed report submission, including SOP document. | 2019-08-13 | 2019-08-13 | Afforestt |  | O
8 | Potential Native Vegetation (PNV) Database and preliminary research documentation submission. | 2019-08-06 | 2019-08-13 | Afforestt |  | O
9 | Field Research at Sanjay Gandhi National Park for primary data collection, and secondary data collection and validation. | 2019-07-24 | 2019-08-22 | Afforestt |  | O
10 | Submission of BOM including site preparations, quality and quantity specifications of all consumable and non-consumables, watering and maintenance requirements, Nursery set-up requirements and site-office requirements. | 2019-08-06 | 2019-08-18 | Afforestt |  | O
11 | Maintenance SOP submission. | 2019-08-06 | 2019-08-18 | Afforestt |  | O
12 | Execution SOP and videos submission, including earthwork and soil preparation. | 2019-08-06 | 2019-08-18 | Afforestt |  | O
13 | Submission of SOP for Sapling arrangement, layering and distribution. | 2019-08-06 | 2019-08-18 | Afforestt |  | O
14 | Submission of species selection, quantification and order list. | 2019-07-24 | 2019-09-01 | Afforestt |  | O
15 | Submission of quality specifications of saplings. | 2019-07-24 | 2019-09-01 | Afforestt |  | O
16 | SOP and explainer documents for species selection and quantification. | 2019-07-24 | 2019-09-01 | Afforestt |  | O
17 | Provide vendor contacts for key materials - husk, cocopeat, straw, manure, jeevamrit, ghan jeevamrit and bamboo. | 2019-08-29 | 29/08/19 | Afforestt |  | O
18 | Provide vendor contacts for saplings and initiate communication to finalise orders. | 2019-08-29 | 2019-09-01 | Afforestt |  | O
19 | Final masterplan drawing submission incorporating forest, hardscape and softscape, and suggestions of MCGM officials. | 2019-08-06 | 2019-08-28 | Client |  | O
20 | Finalize forest zones wrt total area, with pathways and open spaces within designated forest zones. | 2019-08-14 | 2019-08-31 | Afforestt |  | O
21 | Execution drawings for forest creation. | 2019-09-01 | 2019-09-10 | Afforestt |  | X
Pre Execution Site Preparations
1 | Watering pipeline plan, design and irrigation system to be marked on the drawing. | 2019-08-07 | 2019-09-10 | Client |  | X
2 | Physically implement and practically demonstrate - Storage of water, connection and circulation to various forest zones from main line, optimal water force checking, leakage proof uninterrupted flow through hose pipes and showers. Total Requirement = 16500 sq m X 4 L = 66,000 L per day. | 2019-09-06 | 2019-09-20 | Client |  | X
3 | Initial buffer stock of red hill earth soil to be maintained on site = 500 cubic meters soil or 100 trucks. | 2019-08-07 | 2019-09-20 | Client |  | X
4 | Nursery area to be prepared as per BOM, with complete infrastructure including watering, and a minimum of 4 workers to manage the nursery until project execution completion. | 2019-09-06 | 2019-09-20 | Client |  | X
5 | Take quotations from suppliers of key materials - husk, cocopeat, straw, manure, jeevamrit, ghan jeevamrit and bamboo. In case of new suppliers, fix up quality checking date at source and accompany Afforestt for checking, or get samples at the site. Finalize order. | 2019-09-09 | 2019-09-23 | Client | Afforestt | X
6 | Take quotations from Saplings suppliers and finalize the final order in close consultation with Afforestt. Finalize order | 2019-09-09 | 2019-09-23 | Client | Afforestt | X
7 | Finalize machinery, manpower, tools and equipments as per BOM for forest creation. Keep in mind semi skilled workers who have some past experience with handling saplings. | 2019-09-09 | 2019-09-30 | Client |  | X
8 | Finalize and block manpower for forest maintenance as per BOM until forest reaches handover stage. | 2019-09-09 | 2019-09-30 | Client |  | X
9 | Designate, demarcate and clean area for biomass stocking. 1500 sq meters, flat ground, clear of weeds/waste/debris. | 2019-09-09 | 2019-09-15 | Client
10 | Receive 50% consignment of biomass - husk, cocopeat, manure, straw. All materials to be covered with tarpaulin sheets. | 2019-09-23 | 2019-09-30 | Client | Afforestt | X
11 | Prepare delivery schedule of Jeeevamrit and Ghan Jeevamrit to ensure freshness. | 2019-09-16 | 2019-09-20 | Afforestt |  | X
12 | Receive 100% consignment of saplings. | 2019-09-23 | 2019-09-30 | Client | Afforestt | X
13 | Receive 50% consignment of bamboo sticks. | 2019-09-23 | 2019-09-30 | Client | Afforestt | X
14 | Receive first batch of Jeevamrit and Ghan Jeevamrit as per usage schedule prepared by Afforestt. | 2019-09-28 | 2019-09-30 | Client | Afforestt | X
15 | Create site office with necessary documentation, display and amenities. Tent set-up at a visible and clean spot preferred to receive and educate MCGM officials and local citizens. | 2019-09-28 | 2019-09-30 | Client | Afforestt | X
16 | Receive, create inventory and stock all other consumables, non consumable items, tools, equipments and personnel protective equipments PPE as per the BOM. | 2019-09-23 | 2019-09-30 | Client |  | X
17 | Set up nursery display boards. | 2019-09-28 | 2019-09-30 | Afforestt | Client | X
18 | Set up labor resting area, with drinking water. | 2019-09-28 | 2019-09-30 | Client |  | X
19 | Functional toilet for workers and other staff on site. | 2019-09-23 | 2019-09-30 | Client |  | X
20 | Prepare distribution plan and system for saplings across the site keeping in mind stock at the site. | 2019-09-23 | 2019-09-30 | Afforestt. |  | X
| Forest Creation (1st phase - 8000 sq m) @ 200 sq meters per day. | 2019-10-01 | 2019-11-20 | Client | Afforestt | X
1 | Demarcation and marking as per execution drawings.
2 | Preparing biomass mixture and distribution calculation.
3 | Mound making.
4 | Sapling distribution and arrangement as per distribution pattern submitted by Afforestt.
5 | Plantation.
6 | Appropriate jeevamrit and ghan jeevamrit application.
7 | Support stick work.
8 | Mulching.
9 | Tying down mulch wherever required.
10 | Finishing, checking, rectifications.
11 | Forest maintenance.
12 | Receive jeeevamrit and ghan jeevamrit as per schedule fixed by Afforestt.
| Receive 2nd and final Batch of materials for forest creation (2nd phase - 8500 sq meters) | 2019-11-10 | 2019-11-20 | Client | Afforestt | X
| Forest Creation (2nd phase - 8500 sq m) @ 200 sq meters per day. | 2019-11-21 | 2019-12-31 | Client | Afforestt | X
1 | Demarcation and marking as per execution drawings.
2 | Preparing biomass mixture and distribution calculation.
3 | Mound making.
4 | Sapling distribution and arrangement as per distribution pattern submitted by Afforestt.
5 | Plantation.
6 | Appropriate jeevamrit and ghan jeevamrit application.
7 | Support stick work.
8 | Mulching.
9 | Tying down mulch wherever required.
10 | Finishing, checking, rectifications.
11 | Forest maintenance.