DESIGN

- Master Plan

WHAT

A master plan clearly indicates the area designated for afforestation.

WHY

The total area for afforestation (in Sq. Mtrs) is to be precisely calculated in order to determine the amount of material required.

Project execution is planned on the basis of the master plan.

WHO

Chief architect of the project.

WHEN

Before we start project preparation.

HOW

Provide the essential requirements of afforestation to the architect and get the area sketched on the master plan.

The essential requirements are:

- Ideally, the Forest should be at-least 4 meters wide for maximum impermeability.

- The minimum width needed for Miyawaki Method of afforestation is 3 meters. However, for best results, the ‘recommended’ width is 4 meters.

Afforestation Area

Built up Area

4 Meters

- Watering Plan

WHAT

Water pipeline layout in order to water the forest.

WHY

For first two-three years, the forest has to be watered regularly.

WHO

Client’s architect or Afforestt’s recommended designer will do the pipeline design.

WHEN

Before we start project preparation.

HOW

A main line has to be designed based on daily water requirement for the entire area, backed by bore wells and overhead tanks.

Essential requirements are.

- The watering facility design has to be made with a main line with watering outlets for hoses, which can reach the entire area of the forest.

- Main line capacity has to be ‘W X A’, where A is Afforestation area in sq. mtrs and W is watering requirement in liters per sq. mtrs per day.

Hose

Main watering line

Watering sub-line

- Project Execution Planning

WHAT

Design for facilities for project execution.

WHY

To complete the execution without compromising on quality standards and for ease of operation.

WHO

Client’s architect or Afforestt’s recommended designer along with an Afforestt consultant.

WHEN

Before we start project preparation.

HOW

Design the following spaces in AutoCAD on the master plan file:

- Material storage area-

- It has to be 10% of the total afforestation area. One material storage area for every 4,000 sq. mtrs of afforestation area is required.

- Has to be within close proximity of the site.

- Approach road from storage area to afforestation area is essential.

- Saplings storage area-

- It has to be 5% of the total afforestation area. One saplings storage area for every 4,000 sq. mtrs of afforestation area is required.

- Has to be within close proximity of the site.

- Approach road from storage area to afforestation area is essential.

- Site office-

- Should have easy access to the entire afforestation area.

- Should have road connectivity to the entrance of the property.

- Resting area for the labor-

- Covered area with drinking water facility and sitting area for meals.

- Should have washing area and toilets.

- Tools and equipment storage area.

- Protected from rain and wind.

- Access to designated personnel only.

- Approach roads to the afforestation area for earthmover access.

- Approach roads to the material storage area and saplings storage area with truck access.

4

5

2

1

7

3