Solid Waste Plants Not Operational (under construction/land dispute/dispute with operator etc.)

20 No.Total Capacity-4155 TPD

| S.No | Status | No. | Place and Capacity- (TPD) | Type | Reason/Remark |
| --- | --- | --- | --- | --- | --- |
| 1 | Under construction | 01 | Jaunpur-80 | Waste to Compost | Concesionaire needs pending amount. |
| 2 | Retendering & Agreement done | 04 | Bareilly-300 | Waste to Compost | NGT Case going on. |
|  |  |  | Moradabad-280 |  | Land Dispute. |
|  |  |  | Agra-750 | Waste to Energy | NOC from TTZ pending. |
|  |  |  | Meerut-600 |  | - |
| 3 | Retendering proposed | 02 | Gorakhpur-500 | Waste to Compost | Under Tendering |
|  |  |  | Jhansi-300 |  | Under Tendering |
| 4 | Dispute with operator | 06 | Mathura-180 | Waste to Compost | - |
|  |  |  | Fatehpur-55 |  | Arbitration |
|  |  |  | Sambhal-75 |  | - |
|  |  |  | Badaun-55 |  | Arbitration |
|  |  |  | Mirzapur-100 |  | Arbitration |
|  |  |  | Ballia-40 |  | Arbitration |
| 5 | Land not available | 03 | Firozabad-130 | Waste to Compost | Land not available |
|  |  |  | Basti-40 |  | - |
|  |  |  | Nazibabad-60 |  | - |
| 6 | Land Dispute | 03 | Ghaziabad-300 | Waste to Compost | Matter with Hon'ble Supreme Court. |
|  |  |  | Bhadohi- 40 |  | Land Dispute |
|  |  |  | Loni-120 |  | Land Dispute |
| 7 | Lease Agreement | 01 | Rampur-150 | Waste to Energy | Lease Agreement Pending |

If above mentioned MSW Treatment Facilities become operational then the total treatment capacity will increase to 8770 TPD (4615 TPD +4155 TPD)..