## STEP 6 - BOM
Afforestation-Project Execution BOM for Kanha Forest Creation Workshop | [6 empty] | Cynthia Sinclair 14-02-2019
Afforestation Area (Fixed) | 125 | Sq. Mtrs. |  | Project execution Start date |  | 2019-02-13
Plantation Density (Fixed) | 3.2 | Saplings Per Sq Mtr |  | Project execution End Date |  | 2019-02-15
Execution Time (Variable) | 3 | Days |  | Working hours per day (Man) |  | 8
Daily Area Covered During Earth Work | 41.6667 | Sq. Mtrs. |  | Working hours per day (Machine) |  | 8
Number of Trees Planted | 400 | Number |  | Afforestt's Personnel on Site |  | 4
Estimated project cost |  |  | INR | 118500
Cost per Sq Mtr |  |  | Rs. Per Sq Mtr | 948
Bill of Material
Man n Machine | Qty | Material | Unit | Qty | Tools | Qty | Safety Gear | Qty | Facilities | Qty
JCB- 3DX | 1 | Husk | Ton | 1 | Plastic Cutter | 8 | Gloves | 8 | Saplings storage area | 1
Tipper | 1 | Jeevamrutha | Liters | 100 | Pans | 8 |  |  | Material Storage Area | 1
Mandays | 24 | Manure | Ton | 2.5 | Buckets | 8 |  |  | Safety Fencing | 1
|  | Ghana Jeevaamrutha | Kg | 200 | Trovel | 8 |  |  | Hose pipe + Shower | 1
|  | Mulch | Ton | 1 | Hoe | 8
|  | Saplings | Numbers | 400 | Gardening rake | 8
|  | Support Sticks | Numbers | 400 | Mugs | 8
|  | Pegs | Numbers | 30
|  | Support stick rope | Meters | 100
|  | Lime Stone Powder | Kg | 30
|  | Tying rope for mulch | Meters | 200
|  | Stickers for saplings | Numbers | 40
Cost Estimation
Item | Unit Per Sq Mtr | Unit | Unit Cost | Unit Qty Per day | Per day cost | Total Unit Qty | Total Cost
[9 empty] | Item |  | Per worker | Unit | Unit Cost | Total Qty | Total Cost
Man n Machine | [6 empty] | 31200 |  | Material-Tools and Equipments | [5 empty] | 6400
JCB- 3DX | 0.192 | Hours | 800 | 8 | 6400 | 24 | 19200 |  | Plastic Cutter |  | 1 | Numbers | 20 | 8 | 160
Tipper | 0.192 | Hours | 200 | 8 | 1600 | 24 | 4800 |  | Pans |  | 1 | Numbers | 200 | 8 | 1600
Manpower | 0.192 | Mandays | 300 | 8 | 2400 | 24 | 7200 |  | Buckets |  | 1 | Numbers | 100 | 8 | 800
[9 empty] | Trovel |  | 1 | Numbers | 80 | 8 | 640
[9 empty] | Hoe |  | 1 | Numbers | 200 | 8 | 1600
Material- Consumables | [6 empty] | 59500 |  | Gardening rake |  | 1 | Numbers | 175 | 8 | 1400
Husk | 0.008 | Ton | 6000 | 0.33333 | 2000 | 1 | 6000 |  | Mugs |  | 1 | Numbers | 25 | 8 | 200
Jeevamrutha | 0.8 | Liters | 25 | 33.3333 | 833.3333 | 100 | 2500
Manure | 0.02 | Ton | 5000 | 0.83333 | 4166.6667 | 2.5 | 12500 |  |  |  | Per worker | Unit | Unit Cost | Total Qty | Total Cost
Ghana Jeevaamrutha | 1.6 | Kg | 25 | 66.6667 | 1666.6667 | 200 | 5000 |  | Safety Gear | [5 empty] | 400
Mulch | 0.008 | Ton | 6000 | 0.33333 | 2000 | 1 | 6000 |  | Gloves |  | 1 | Numbers | 50 | 8 | 400
Saplings | 3.2 | Numbers | 50 | 133.3333 | 6666.6667 | 400 | 20000
Support Sticks | 3.2 | Numbers | 15 | 133.3333 | 2000 | 400 | 6000 |  | Item |  | Per Site | Unit | Unit Cost | Total Qty | Total Cost
Pegs | 0.24 | Numbers | 5 | 10 | 50 | 30 | 150 |  | Facilities-Fixed | [5 empty] | 21000
Support stick rope | 0.8 | Meters | 2 | 33.3333 | 66.6667 | 100 | 200 |  | Saplings storage area |  | 1 | Number | 0 | 1 | 0
Lime Stone Powder | 0.24 | Kg | 5 | 10 | 50 | 30 | 150 |  | Material Storage Area |  | 1 | Number | 0 | 1 | 0
Tying rope for mulch | 1.6 | Meters | 4 | 66.6667 | 266.6667 | 200 | 800 |  | Safety Fencing |  | 1 | Numbers | 20000 | 1 | 20000
Stickers for saplings | 0.32 | Numbers | 5 | 13.3333 | 66.6667 | 40 | 200 |  | Hose pipe + Shower |  | 1 | Numbers | 1000 | 1 | 1000